## Test Case Template 1
GIDS: Add Partial Match Functionality to Crosswalk Issues Table
|  | Execution Summary |  | Additional Notes
Test Case Id: | #5638
Test Cases Folder | Sprint 40 | Tested by: Adam Sonntag
Story ID: | #4362
Test Case written by: | Adam Sonntag | Date Completed: 02/07/2020
Setup/ Pre-conditions
Details: | As an EDU Team Member, I need the ability the ability to see a potential list of IPEDSHD entries that match the WEAMS facility code to reduce the manual effort involved in updating the crosswalk.
Branch | bah-4362
Environment: Local
Section | Test Step/Substep | Expected Result | Actual Result | Pass/Fail | Defect # (make # a link) | Browser Tested on | Device tested on | Bug Resolution | Notes
| Access localhost:4000 and log in | GIDS Dashboard is displayed | As Expected | Pass |  | Chrome | Desktop
| Select Crosswalk Partial Issues tab at top | Crosswalm Partial Issues displays | As Expected | Pass |  | Chrome | Desktop
| There is a "Find" action available in the Crosswalk Issues table. | Find action available | As Expected | Pass |  | Chrome | Desktop
| When the users clicks "Find", the following results are returned: a. WEAMS "institution name" entries that fuzzy match the IPEDS HD "instnm" entries. b. WEAMS "address" (1, 2, 3, city, state, zip) entries that fuzzy match the IPEDS HD "address" (addr, city, stateabbr, zip) entries. c. WEAMS "physical address" (1, 2, 3, city, state, zip) entries that fuzzy match the IPEDS HD "address" (addr, city, stateabbr, zip) entries. | WEAMS "institution name" entries that fuzzy match the IPEDS HD "instnm" entries, WEAMS "address" (1, 2, 3, city, state, zip) entries that fuzzy match the IPEDS HD "address" (addr, city, stateabbr, zip) entries, WEAMS "physical address" (1, 2, 3, city, state, zip) entries that fuzzy match the IPEDS HD "address" (addr, city, stateabbr, zip) entries. | As Expected | Pass |  | Chrome | Desktop
| The following details are displayed: Weams Institution Name Weams Full Address Weams Full Physical Address IPEDS Institution Name IPED Full Address IPEDS OPEID IPEDS IPED ID | All Details are properly displayed | As Expected | Pass |  | Chrome | Desktop
| The user can: a. Select an entry to match with. | The option to match is available | As Expected | Pass |  | Chrome | Desktop
| The user can: b. Cancel without choosing a matching entry. | The option to cancel is available cancelling the match selection | As Expected | Pass |  | Chrome | Desktop
| If the user selects an entry to match: a. If a crosswalk entry exists, the entry is updated with the IPEDS data. b. If a crosswalk entry does not exist, an entry is created with the IPEDS data. c. The row is removed from the "Ipeds issues" table | All options occur | As Expected | Pass |  | Chrome | Desktop
| If the user does not confirm the association, no action is taken. | No action is taken | As Expected | Pass |  | Chrome | Desktop
Environment: Staging
Section | Test Step/Substep | Expected Result | Actual Result | Pass/Fail | Defect # (make # a link) | Browser Tested on | Device tested on | Bug Resolution
Environment: Production
Section | Test Step/Substep | Expected Result | Actual Result | Pass/Fail | Defect # (make # a link) | Browser Tested on | Device tested on | Bug Resolution

## Sheet1
Pass | IE | Desktop | Fixed
Fail | Chrome | Phones | Not Fixed
N/A | Firefox | Tablet | Will Not Fix
Blocked | Safari | Desktop and Phones | Closed
| Opera | All | Duplicate
| Chrome, FF and IE |  | NAB (Not a bug)
| Chrome and Safari |  | Out of Scope
| Chrome and IE |  | Change order
Chrome and Firefox
Chrome, IE and Firefox
All