## Sheet1
ID | Description | Owner | Date Initiated | Date Completed | Status
1 | Build APIs for Vets.gov a. /DocServices + /Claims Services + /eFolder b. /Post911 GI Bill c. /Letters d. /Disability (526 suite of forms) e. /ITF f. /Add /Modify Dependents (686/674) g. /Request for State Benefits h. /VRE [Forms 1990:8832] i. /Payment History j. /VLER [VAPii] | Paul | 2017-03-29 |  | In Progress - EVSS to complete Doc Services and Claim Status APIs (will support eFolder); re-ordered based on conversation with Julie; prioritize VA Letters & Post-911 GI Bill ahead Disability.
1.5 | Keep priority list in a shared place | Julie | 2017-04-18 | 2017-04-19 | CLOSED - A pinned post in the #evss Slack channel contains the current priority. This post is editable by all. We will use the post for reference in standups and meetings; it should not change without real discussion with everyone. If this doesn't work/isn't working, we'll reevaluate as a group.
2 | UX for eBenefits/Vets.gov login | Julie | 2017-03-29 | 2017-04-28 | CLOSED: We will keep logins separate and follow existing interaction patterns e.g. with Vets.gov and MHV. Open - Julie to work with UX and come to a decision about investing effort in federated logins or keeping separate and follow existing interaction patterns e.g. with Vets.gov and MHV.
3 | Crossreference our ID.me + MVI user object and the traits needed by EVSS | Julie | 2017-03-29 |  | 5/1: Open - Josh has sent list, Julie is reconciling (will send back 5/1) * Questions still under discussion: Do we pass the assertion or something that decrypts that? How do we want to do the validation of the token; do we just trust or do validation? (see #14). Can we get VAFii out of the mix? Julie and Josh L to reconcile the lists. * Josh L to send traits neded. * Questions: Do we pass the assertion or something that decrypts that? How do we want to do the validation of the token; do we just trust or do validation? (see #14). Can weget VAFii out of the mix?
4 | Build end service layers on top of service layers | Paul | 2017-03-29 | 2017-03-29 | CLOSED - Decision from 3/29. These will become individual epics.
5 | Ensure clarity on priority process for moving items to Vets.gov | Julie | 2017-03-29 | 2017-04-18 | CLOSED - Decision on 4/18 was to continue to communicate in daily standup and on slack, Elisa and Paul to keep a master EVSS roadmap document. No changes in prioritization unless at least Elisa, Paul, Julie, Josh L have a chat.
6 | How to move forward to leverage significant Technical architecture investments that DS has been able to implement within the VA? | Julie | 2017-03-29 | 2017-03-30 | CLOSED - Receiving the TRM list covers this issue
7 | EVSS would cleanup documentation to be API driven. Claims and Doc APIs are currently being worked | Paul | 2017-03-29 | 2017-03-29 | CLOSED - Decision from 3/29. The epic for each service will include documentation that will be API driven.
8 | Move to target state architecture for APIs in AWS Cloud. Agree on guiding principals for the future state of EVSS as part of the vets.gov solution. | Josh L | 2017-03-29 | 2017-03-29 | CLOSED - This is a statement that is part of the approach for who EVSS architected and subsequently utilized by vet.gov. Other statements include: • Move EVSS capabilities to APIs/microservices • Atomic domain that can be moved and run on AITC or GovCloud • Move APIs to AWS/GovCloud. • Incorporate composite APIs as a core part of the vets.gov interface • Vets.gov will handle inflight data • Trust boundary: establish a token that is shared between systems. Forward SAML token that is signed. Pass it on every request. User is a transitive trust - wrap MVI data and pass it thru. Define the correlation ids that EVSS needs and let vets.gov know.
9 | Need to determine how to leverage devops across the program, specifically to support replatforming on Vets.gov (AWS) servers | Alex | 2017-03-29 |  | 5/1: BLOCKED by NSOC. Josh L provided cURL script that Vets.gov needs to run from AWS to get timing data to backend VA systems. Blocked by Transit VPC not being able to connect to VA network. That issue should be resolved this week so we can have data showing if GovCloud is slower to connect to VA backend services than EVSS currently, which will then determine next steps. Open - Starting conversation in 4/18 meeting with Dan's presentation and next steps.
10 | Determine AWS bandwidth for supporting a unified Production environment | Alex | 2017-03-29 |  | 5/1: DSVA is meeting internally this week (on 5/4) to discuss path forward on how to get to Direct Connect in production, which will then determine what the AWS setup will need to look like (at which point we will likely need to involve Angela). Open - More of a contract question than anything else.
11 | Devops and GovCloud parallel test need to occur | Josh L | 2017-03-29 |  | DEFER - need GovCloud operating environment complete with connections through VA Firewall
12 | Pre-population occurring by eBenefits and Vets.gov. Need to identify correct data source for fetching data. | Julie | 2017-03-29 |  | Open - Need to map which forms would prepopulate from benefits or heath (identity correct canonical source); EVSS to provide load ops
13 | Determine how to update veteran centric data (address, DD EFT, etc.) based on Veteran | Julie | 2017-03-29 |  | Open - Bigger conversation needed, essentially the question is how to act as Vet360 until Vet360 exists.
14 | Establish trust boundary/requirements for Vets.gov | Josh/Julie | 2017-03-29 |  | 5/1: In Progress. Josh L sent document to Julie and Julie is reviewing. Open - Alex and Josh L work together on this
15 | Determine what to do with Digit-2-Digits (D2D). | Angela | 2017-03-29 |  | Open - Angela to have discussion with this team to find new place for this
16 | Change management and communication plan needs to start in parallel with planning for migration of capabilities to Vets.gov | Julie | 2017-03-29 |  | Open - This big action item should be converted to smaller items that corresponding with veteran functionality being migrated.
17 | Identify features for the eBenefits capabilities that should not be included in the migration to Vets.gov for discussions with business stakeholders | Paul | 2017-03-29 | 2017-04-18 | CLOSED. In the F2F meeting the following were defined as not in scope of the migration to vets.gov, and are now confirmed as out of scope: • Appeals • Early Communications • D2D • CRM account history • MHV form (10-5345a-MHV) • SGLI • VGLI • Appointments • eFolder #2
18 | (4142/a) - authorization to disclose information - needs a signature. | Julie | 2017-03-29 |  | Open - When doing disability product discovery, will determine the proper treatment of this (ask the Veteran if they have records? Are they attaching them to the claim? If not, then submit 4142/a)
19 | (686/674) - Should have an option to upload this as part of the disability claim or fill this out. This would then go to eFolder to be part of the rating review | Julie | 2017-03-29 | 2017-04-18 | CLOSED. This is a functional requirement that was not implemented in VDC. This will be part of the dicovery for 686/674.
20 | VLER (VaPii) Need to do discovery | Julie | 2017-03-29 |  | Defer to later discovery; this is not prioritized currently.
21 | VSO Search (OGC DB) . Vets.gov may go direct to data | Julie | 2017-03-29 |  | Defer to later discovery; this is not prioritized currently.
22 | Person/Profile - PCIU - Needs shared discovery | Julie | 2017-03-29 |  | Defer to later discovery; this is not prioritized currently.
23 | Appeals: will not be using EVSS APIs for that. | Julie | 2017-03-29 |  | Open - Vets.gov to plan decommission change management and communication plan once on vets.gov
24 | Early Communications | Julie | 2017-03-29 |  | Open - Investigate recent decision on business decision to turn this off entirely. Josh Q has emailed Mike Carr. IF remaining a thing, Vets.gov review list of notifications, define f/e requirements. Talk to BAS and Denise about this. Currently an out of scope item.
25 | CRM account history | Paul | 2017-03-29 |  | 5/1: : Defer until Joint Discovery is targeted; we will need to involve Chris Accolla (CRM-contractor) to understand why CRM is using eBenefits Account HistoryIn Progress - EVSS to find out how they are using this? Need to do some discovery. Currently an out of scope item.
26 | MHV form (10-5345a-MHV) | Alex | 2017-03-29 |  | 5/1: In Progress. DSVA meeting with the Privacy Office and General Counsel on this Friday (5/5). Still on track but will not be totally completed until we launch “MHV account creation” on Vets.gov in June and don’t need/use this form. Open. Make this go away based on fact that veteran is logged in as LOA3 (policy work)
27 | SGLI - Action: Vets.gov. go to Milconnect. SAML reassertion. Action: EVSS define how we will get to this data | Julie | 2017-03-29 |  | Open. Go to Milconnect w/ SAML reassertion. EVSS define how we will get to this data. Currently an out of scope item but not off the table.
28 | VGLI | Julie | 2017-03-29 |  | Open. Vets.gov Content page with link to VGLI info is current plan, anything else is out of scope.
29 | Appointments: | Julie | 2017-03-29 |  | Open. Vets.gov is doing this through MHV; no EVSS work. Comms plan to decommission once on Vets.gov should go to Natalie Moore on DSVA team.
30 | eFolder v2 | Angela | 2017-03-29 |  | Open. Angela to direct to Denise VE input process. Curently an out of scope item.
31 | iFrames/SAML assertions | Julie | 2017-03-29 |  | DELETE LINE ITEM. Broken out to individual action items.
32 | Doc Services and Claims Services | Paul | 2017-03-29 |  | 5/1: New Diagram in progress and will be shared that provides more detailed timing for Vets.gov to consume new API / VBMS eFolder services In Progress. Diagram shown on 4/18/17, API review offline.
33 | Disability Discovery architectural pattern | Josh L | 2017-03-29 |  | Defer. Integration pattern to be confirmed with Alex when 526 Joint Discovery commences
34 | ITF Requirements | Josh L | 2017-03-29 |  | Open. Josh L & Josh Q to discuss
35 | Vets.gov to point to new doc service end point | Josh Q | 2017-03-29 |  | In Progress.
36 | DevOps conversations between Alex and Josh L. | Alex | 2017-03-29 |  | DELETE LINE ITEM. Same as #9.
37 | SEP solution | Paul | 2017-03-29 |  | In Progress. Discovery starting with existing functional requirements
38 | LGY: COE: Certificate of Eligibility for Home loans | Josh Q | 2017-03-29 |  | Open. Josh Q to ask LGY to build endpoint or otherwise come up with a solution. Not a high prioritization.
39 | LGY: SHA/ SAH: Special Housing Adaptation/Specialty adaptive housing | Josh Q | 2017-03-29 |  | Open. Josh Q to ask LGY to build endpoint or otherwise come up with a solution. Not a high prioritization.
40 | DoD: DPRIS - Defense Personnel Request Info Systems | Julie | 2017-03-29 |  | Open. Vets.gov to define approach. Not a high prioritization.
41 | VHA: FRIP/ICP - Interagency Compensation Plan | Julie | 2017-03-29 |  | Open. Vets.gov to define approach, but we all pretty much think EVSS should wrap the API. Not a high prioritization.
42 | EDU: CH33 - Chapter 33 Enrollment Status (CH33 exists) | Josh Q | 2017-03-29 |  | Open. Vets.gov to look to see if the current CH33 services can be used. Not a high prioritization.
43 | WAVE: Mont. GI Bill Verification | Julie | 2017-03-29 |  | Open. Vets.gov to define approach. Not a high prioritization.
44 | ROES (heading aid Batteries and Prosthetic socks) | Julie | 2017-03-29 |  | Open. Vets.gov to define approach. Not a high prioritization.
45 | Build VA Letters API | Paul | 2017-04-18 |  | Open. Build API for letter service that provides back only the letters appropriate for the given user
46 | VA Letters - review forced validation requirements and metrics | Josh L | 2017-04-18 |  | Open. Maybe monitor for a time via Google Tag Manager to understand if this is needed for an MVP. Key is to understand if we need to allow for the address update before the letter is generated.
47 | VA Letters - Benefits Summary Letter has checkboxes, need to check if this is needed | Josh L | 2017-04-18 |  | Open.
48 | Add CoE Letter for Education | Josh Q | 2017-04-18 |  | Open. Josh Q to get letter signed off on and provide data to EVSS re: content
49 | Determine need to build Roles service | Josh L | 2017-04-18 |  | Open.
50
51
52
53
54
55