## Test Case Template 1
GIDS: Allow user to update crosswalk values for WEAMS data that has an IPED or OPE match
|  | Execution Summary |  | Additional Notes
Test Case Id: | #5306
Test Cases Folder | Sprint 39 | Tested by: Michael Delli-Gatti
Story ID: | #4751
Test Case written by: | Michael Delli-Gatti | Date Completed: 01/30/2020
Setup/ Pre-conditions | have WEAM, IpedHD and Crosswalk files uploaded to GIDS
Details: | As an EDU Team Member, I need the ability to link the Dept of Education IPEDS data to the VA EDU Services WEAMS data so that the correct information is displayed on the Comparison Tool Profile Page.
Branch | bah-crosswalk-fix
Environment: Local
Section | Test Step/Substep | Expected Result | Actual Result | Pass/Fail | Defect # (make # a link) | Browser Tested on | Device tested on | Bug Resolution | Notes
| access localhost:4000 and log in | GIDS Dashboard is displayed | As Expected | Pass |  | Chrome | Desktop
| Click Crosswalk Partial Matches at the top of the page | Crosswalk issues page is displayed with a new Action column that contains an Edit button for each institution | As Expected | Pass |  | Chrome | Desktop
| Click Edit for any institution | Crosswalk single issue page is displayed with all known data from each file (weam, ipedhd, and crosswalk) displayed in three separate tables | As Expected | Pass |  | Chrome | Desktop
|  | 4 buttons are present at the bottom of the page: Update crosswalk from WEAMS Update crosswalk from IPEDS Clear IPEDS/OPE Update | As Expected | Pass |  | Chrome | Desktop
|  | If there is no data from the IPEDS file, the button to use the data from that file is disabled | As Expected | Pass |  | Chrome | Desktop
| Click Clear IPEDS/OPE | The IPEDS and OPE columns of the Crosswalk table are cleared | As Expected | Pass |  | Chrome | Desktop
| Click update | The record is saved | As Expected | Pass |  | Chrome | Desktop
| Return to the crosswalk issues table | The record had been updated in this table as well | As Expected | Pass |  | Chrome | Desktop
| Click Edit for an institution that has values for the two IPEDS HD columns and the two corresponding WEAMS columns which matches, but not the Crosswalk columns | Crosswalk single issue page is displayed with values in the IPEDS HD table | As Expected | Pass |  | Chrome | Desktop
| Click Update Crosswalk from IPEDS | The IPEDS and OPE columns of the Crosswalk table are populated with the information from the IPEDS HD table | As Expected | Pass |  | Chrome | Desktop
| Click Update | Record is saved successfully and user is returned to the crosswalk issues page. The record is no longer present in the table. | As Expected | Pass |  | Chrome | Desktop
| Click Edit for an institution that has all WEAMS column populated with information that does not match the IPEDS columns | Crosswalk single issue page is displayed with values in the IPEDS and OPE columns of the WEAMS table | As Expected | Pass |  | Chrome | Desktop
| Click Update Crosswalk from WEAMS | Crosswalk table is upated with data from the WEAM table | As Expected | Pass |  | Chrome | Desktop
| Click Update | Record is updated successfully | As Expected | Pass |  | Chrome | Desktop
| Return to the crosswalk issues table | Record is still present in the Crosswalk Issues table because the IPEDS information does not match the WEAMS information. The information for the crosswalk columns has been upated | As Expected | Pass |  | Chrome | Desktop
| Click Edit for an institution that has all WEAMS column populated and no IPEDS information | Crosswalk single issue page is displayed with values in the IPEDS and OPE columns of the WEAMS table and no information in the IPEDS HD table | As Expected | Pass |  | Chrome | Desktop
| Click Update Crosswalk from WEAMS | Crosswalk table is upated with data from the WEAM table | As Expected | Pass |  | Chrome | Desktop
| Click Update | Record is updated successfully | As Expected | Pass |  | Chrome | Desktop
| Return to the crosswalk issues table | Record is updated in the crosswalk issues table | As Expected | Pass |  | Chrome | Desktop
| Click Edit for any institution | Crosswalk single issue page is displayed | As Expected | Pass |  | Chrome | Desktop
| Manually edit the IPEDS and OPE values in the crosswalk table and click update | Record is updated successfully | As Expected | Pass |  | Chrome | Desktop
| Return to the crosswalk issues table | Record is updated in the crosswalk issues table | As Expected | Pass |  | Chrome | Desktop
Environment: Staging
Section | Test Step/Substep | Expected Result | Actual Result | Pass/Fail | Defect # (make # a link) | Browser Tested on | Device tested on | Bug Resolution
Environment: Production
Section | Test Step/Substep | Expected Result | Actual Result | Pass/Fail | Defect # (make # a link) | Browser Tested on | Device tested on | Bug Resolution

## Sheet1
Pass | IE | Desktop | Fixed
Fail | Chrome | Phones | Not Fixed
N/A | Firefox | Tablet | Will Not Fix
Blocked | Safari | Desktop and Phones | Closed
| Opera | All | Duplicate
| Chrome, FF and IE |  | NAB (Not a bug)
| Chrome and Safari |  | Out of Scope
| Chrome and IE |  | Change order
Chrome and Firefox
Chrome, IE and Firefox
All